## README
Last Update | 2018-10-12
Author | Annie Chiou
Email | achio002@ucr.edu
Description | Tasker Web App
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Registration and Login / Logout | As a person interested by Tasks, I want to register so I can login/logout, and as a registered user, I want to be able to login to fully use the website and to logout once I’m done. | 4 | 3
2 | Create/Add Tasks | As a registered user, I want to be able to create or add tasks so I can keep in mind what I have left to do and to divide it into subtasks so I can detail the task I’m creating/adding. | 3 | 1
3 | Review Tasks | As a registered user, I want to be able to review my created tasks, so I can mark/unmark tasks as complete, edit details, and delete tasks as my schedule changes or if I make mistakes. | 4 | 2
4 | Organize Tasks | As a registered user, I want to be able to group my tasks into different lists, so I can easily find related tasks. Lists are comprised of related tasks. | 4 | 5
| Total |  | 15

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Tasks DAO and DB Mappings
Task 2: Add Task API
Task 3: Add Task Design
Task 4: Edit Tasks API
Task 5: Edit Tasks Design
Task 6: Delete Task Design
Task 7: Delete Task API
Task 8: List Design
Task 9: Add List API
Task 10: User Registration API
Task 11: User Authentication
Task 12: User Logout API
Task 13: Logout Function
Task 14: Delete List API
Task 15: Delete List Design
Task 16: Registration and Login Page
Task 17: Lists DAO and DB Mappings

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Annie Chiou | 7
2 | Annie Chiou

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 15 | 0 | 0 | 15 | 15
1 | 15 | 0 | 0 | 15 | 10
2 | 15 |  |  |  | 5
3 | 15 |  |  |  | 0