## README
Last Update | 2018-10-12
Author | Cheng Chen, Annie Chiou, Ziyi Huang, Geng Wang
Email
Description | Team: Taskers (Cheng Chen, Annie Chiou, Ziyi Huang, Geng Wang)
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Registration and Login / Logout | As a person interested by Tasks, I want to register so I can login/logout, and as a registered user, I want to be able to login to fully use the website and to logout once I’m done. | 4 | 3
2 | Create/Add Tasks | As a registered user, I want to be able to create or add tasks so I can keep in mind what I have left to do and to divide it into subtasks so I can detail the task I’m creating/adding. | 3 | 1
3 | Review Tasks | As a registered user, I want to be able to review my created tasks, so I can mark/unmark tasks as complete, edit details, and delete tasks as my schedule changes or if I make mistakes. | 4 | 2
4 | Organize Tasks | As a registered user, I want to be able to group my tasks into different lists, so I can easily find related tasks. Lists are comprised of related tasks. | 4 | 5
5 | Set Task Priority | As a registered user, I may have plenty of tasks in my list. In order to manage my tasks well, I hope there will be an option which enables me to choose a priority for my tasks, it will be more convenient for me to choose the task I need to handle. | 2 | 7
6 | Set Deadline for Task | As a registered user, I want to be able to know the remaining time left for finishing each tasks, so I can manage all of my tasks properly. | 2 | 8
7 | Sort Tasks | As a registered user, I want to be able to sort my tasks by deadlines and by priority, so I can see at a glance which tasks are more urgent and need my attention.This way I can better plan my schedule and not worry about tasks that are not high priority. | 1 | 9
8 | Create Groups for Users | As a registered user, I want to form groups with my friends and colleagues, so we can share our tasks and edit our tasks together. | 9 | 4
9 | Set / Send Reminders | As a registered user, I want to be able to be informed of my deadlines, so I won’t forget any tasks unconsciously. | 2 | 10
10 | Completed Tasks | As a registered user, I want to be able to see all of my completed tasks, so I can review them if needed. | 3 | 6
| Total |  | 31

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: My Groups Tasks Design
Task 2: My Groups List Desgin
Task 3: DAO and DB Mappings
Task 4: Create Group API
Task 5: Add Task API
Task 6: Group Join Invite Design
Task 7: Add Task Design
Task 8: Edit Tasks API
Task 9: Edit Tasks Design
Task 10: Delete Task Design
Task 11: Delete Task API
Task 12: List Design
Task 13: Add List API
Task 14: Rename List API
Task 15: Edit List Design
Task 16: Send Email Invite API
Task 17: Group Page Layout
Task 18: Logout Function
Task 19: User Registration API
Task 20: User Authentication
Task 21: User Logout API
Task 22: Delete List API
Task 23: Delete List Design

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Annie Chiou | 7
2 | Annie Chiou

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 31 | 0 | 0 | 31 | 31
1 | 31 | 2 | 2 | 29 | 20.67
2 |  |  |  |  | 10.33
3 |  |  |  |  | 0