## README
Last Update | 2018-10-12
Author | Annie Chiou
Email | achio002@ucr.edu
Description | Tasker Web App
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Registration and Login / Logout | As a person interested by Tasks, I want to register so I can login/logout, and as a registered user, I want to be able to login to fully use the website and to logout once I’m done. | 4 | 3
2 | Create/Add Tasks | As a registered user, I want to be able to create or add tasks so I can keep in mind what I have left to do and to divide it into subtasks so I can detail the task I’m creating/adding. | 3 | 1
3 | Review Tasks | As a registered user, I want to be able to review my created tasks, so I can mark/unmark tasks as complete, edit details, and delete tasks as my schedule changes or if I make mistakes. | 4 | 2
4 | Organize Tasks | As a registered user, I want to be able to group my tasks into different lists, so I can easily find related tasks. Lists are comprised of related tasks. | 4 | 5
| Total |  | 15
Note on C5: Acceptance criteria : - Registered users can create new lists. - Registered users can rename and delete lists. - Registered users can add or delete task(s) from a list.
Note on C4: Acceptance criteria : - Users should be able to edit the description, priority, and subtasks of their existing tasks. - Users can delete tasks or subtasks. - Users can mark or unmark tasks as complete.
Note on C3: Acceptance criteria : - Tasks are created in the list the user is in. By default, if there are no created lists, the created tasks are put in a "My Tasks" list. - Users should be able to add a description, priority, and up to three sub-tasks. - Sub-tasks are only the task action. They do not have a description or priority. - Tasks should be able to be marked as "Complete". The task status is "true" when complete and "false" when not.
Note on C2: Acceptance criteria : - The user should be able to register with his email, choose a username and set a password. - Registered users will log in with their username and their password

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Edit Tasks API
Task 2: Edit Tasks Design
Task 3: Delete Task Design
Task 4: Add List API
Task 5: User Registration API
Task 6: User Authentication
Task 7: User Logout API
Task 8: Logout Function
Task 9: Delete List API
Task 10: Delete List Design
Task 11: Lists DAO and DB Mappings
Task 12: Rename List Design
Task 13: Firebase Migration
Note on D14: (Annie Chiou) Migrate from personal Spring backend to Firebase Acceptance Criteria: 1. Set up DB structure 2. Connect frontend to new APIs
Note on D13: (Annie Chiou) Design list rename button and input for front end Acceptance Criteria: 1. Rename list button 2. Submit 3. Linked to backend api
Note on D12: Annie Chiou Create data access objects and db mappings for backend Acceptance Criteria: 1. DAO files for List tables in DB 2. DB mappings using MyBatis
Note on D11: (Annie Chiou) Design list deletion for front end Acceptance Criteria: 1. Delete list button 2. Confirmation message and submit
Note on D10: (Annie Chiou) Backend support for deleting list Acceptance Criteria: 1. Delete list function 2. Must do so for both user and group lists 3. Update db
Note on D9: Annie Chiou Design logout function 1. Must be able to access from all pages 2. Linked to backend API for ending session 3. Should navigate to home page after logout
Note on D8: (Annie Chiou) Backend support for user logout/ end session 1. Session data should be cleared
Note on D7: (Annie Chiou) Implement authentication in backend (consider using Shiro) 1. Must be able to correctly authenticate user login details from db
Note on D6: (Annie Chiou) Backend support for user registration Acceptance Criteria: 1. User class and interface 2. Update DB correctly with new user data entry
Note on D5: (Annie Chiou) Backend support for creating/ adding list Acceptance Criteria: 1. Implement support for adding list to db 2. List class and interface
Note on D4: Annie Chiou Frontend delete task design Acceptance Criteria: 1. Delete task button 2. Confirmation message and submit button
Note on D3: Annie Chiou Frontend edit tasks design Acceptance Criteria: 1. Edit task button 2. Edit task form with options for task name, priority, deadline, and description.
Note on D2: (Annie Chiou) Backend support for editing tasks Acceptance Criteria: 1. Edit task name, priority, deadline, and description support methods 2. Update db entry

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Annie Chiou | 7
2 | Annie Chiou | 13
3 | Annie Chiou | 6

## Burndown Chart
sk | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 15 | 0 | 0 | 15 | 15
1 | 15 | 2 | 2 | 13 | 10
2 | 15 | 3 | 5 | 10 | 5
3 | 15 | 10 | 15 | 0 | 0